## Instructions
#VALUE! | Urban Watershed Stewardship Grant Program Schedule Instructions
1. Download and save this excel file with the project name you applying for included in the title (do not save as a PDF). 2. Identify the schedule tab for the application track your project is applying for, Stewardship or Infrastructure. Delete the non relevant application track schedule tab. 3. Read the red text at the top of the work plan tab for detailed instructions on how to complete the schedule. 4. Fill in all project activities and key milestones for completing the project scope of work. This should be a detailed list of all planned project activities and should align with the budget requests. For example, if there is a line item for outreach and engagement tasks then these tasks should be clearly outlined in the project schedule. If you have any issues with this spreadsheet reach out to the grant administrator at wsg@sfwater.org 5. Create the schedule with start dates and end dates for each activity . Ensure that project sequencing and timelines are realistic and take into account outside variables such as permitting approvals, scheduling constraints, seasonal limitations, etc. 6. Once the schedule is complete, save the final version as an excel file (do not save as a PDF). Then upload as part of the Urban Watershed Stewardship Grant application package via the application link at sfpuc.gov/wsgrants.

## Infrastructure Track Schedule
This template is where you will outline activities of your proposed project schedule. Please include all activities related to the budget requests including for planning, design, outreach and engagement, construction, etc. Enter start and completion dates for each activity and the duration will autopopulate based on those dates. Ensure that activity dates and duration are accurate and take into account set timelines. For example, SFPUC design reviews will take 30 days on average and permit review timelines can be found online at the appropriate agency websites. The schedule must propose starting construction of the project within 2 years after execution of the Grant Agreement. The activities listed below are a summary of the basic required acitivities needed to deliver a project, but you should add, edit and adjust these as needed.
Infrastructure Track Schedule
Project Name:
Activity | Start Date | End Date | Duration (days) | Staff Lead | Notes
Grant Agreement Execution | 2027-04-01 | 2027-04-30 | 29
Outreach Milestone |  |  | 0
Planning and Design |  |  | 0
30% Construction Design Development |  |  | 0
SFPUC Review of 30% Design Submittal (30 days) |  |  | 0
90% Construction Design Development |  |  | 0
SFPUC Review of 90% Design Submittal (30 days) |  |  | 0
100% Construction Design Development |  |  | 0
SFPUC Review of 100% Design (14 days) |  |  | 0
Permit submittal (list all required permits) |  |  | 0
Permit review (list all required permits) |  |  | 0
Bid and Contractor Selection |  |  | 0
Construction |  |  | 0
Construction milestone |  |  | 0
Construction Milestone |  |  | 0
Reporting/ Invoicing |  |  | 0
Final Site Visit |  |  | 0
Permitting approval (list all required permits) |  |  | 0
0
0
0
0
0
0
0
0
Formulas:
Duration (days) = DAYS([End Date],[Start Date])

## Stewardship Track Schedule
This template is where you will outline activities of your proposed project schedule. Please include all activities related to the budget requests including for planning, design, materials development, outreach and engagement, etc. Enter start and completion dates for each activity and the duration will autopopulate based on those dates. Ensure that activity dates and duration are accurate and take into account set timelines. For example, SFPUC design reviews will take 30 days on average and permit review timelines can be found online at the appropriate agency websites. Below are some example activities that may be included as part of the project schedule. The activities listed below are examples of the activities that may be relevant to deliver a project, please edit these to fit your scope.
Stewardship Track Schedule
Project Name:
Activity | Start Date | End Date | Duration (days) | Staff Lead | Notes
Grant Agreement Execution | 2027-04-01 | 2027-04-30 | 29
Outreach Milestone |  |  | 0
Planning & Design |  |  | 0
Materials Development |  |  | 0
SFPUC Deliverable Review (30 days) |  |  | 0
Activation event |  |  | 0
Permits (list any required permits) |  |  | 0
Installation |  |  | 0
Activation event |  |  | 0
Invoicing/reporting |  |  | 0
Final Close-Out Meeting |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Duration (days) = DAYS([End Date],[Start Date])